## landmark_challenge
Id | Title | Labels | Iteration | Iteration Start | Iteration End | Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | URL | Owned By | Owned By
157563352 | Add basic authentication for users | authentication | 1 | 2018-05-14 | 2018-05-20 | feature | 3 | accepted | 2018-05-14 | 2018-05-14 |  | Daniele Cappuccio | https://www.pivotaltracker.com/story/show/157563352 | Daniele Cappuccio
157602122 | set up testing environment | testing | 1 | 2018-05-14 | 2018-05-20 | chore |  | accepted | 2018-05-15 | 2018-05-15 |  | luca.ferrera96@gmail.com | https://www.pivotaltracker.com/story/show/157602122 | luca.ferrera96@gmail.com
157642834 | models' creation | model | 1 | 2018-05-14 | 2018-05-20 | chore |  | accepted | 2018-05-16 | 2018-05-19 |  | luca.ferrera96@gmail.com | https://www.pivotaltracker.com/story/show/157642834 | luca.ferrera96@gmail.com
157796515 | Add support for OAuth | authentication, oauth | 2 | 2018-05-21 | 2018-05-27 | feature | 2 | accepted | 2018-05-23 | 2018-05-23 |  | Daniele Cappuccio | https://www.pivotaltracker.com/story/show/157796515 | Daniele Cappuccio
157593166 | As Anonymous User, I want to Login with email and password. | authentication, frontend | 2 | 2018-05-21 | 2018-05-27 | feature | 1 | accepted | 2018-05-15 | 2018-05-24 |  | danielepaliotta96@gmail.com | https://www.pivotaltracker.com/story/show/157593166 | danielepaliotta96@gmail.com
157595795 | As Anonymous User, I want to register with email and password. | authentication, frontend | 2 | 2018-05-21 | 2018-05-27 | feature | 1 | accepted | 2018-05-15 | 2018-05-24 |  | danielepaliotta96@gmail.com | https://www.pivotaltracker.com/story/show/157595795 | danielepaliotta96@gmail.com
157819088 | As Anonymous User I want to Register with email, first_name, last_name and password so that I can become a Logged User | backend | 2 | 2018-05-21 | 2018-05-27 | feature | 2 | accepted | 2018-05-23 | 2018-05-24 |  | luca.ferrera96@gmail.com | https://www.pivotaltracker.com/story/show/157819088 | luca.ferrera96@gmail.com
157840373 | OAuth authentication front-end. | authentication, frontend, oauth | 2 | 2018-05-21 | 2018-05-27 | feature | 2 | accepted | 2018-05-24 | 2018-05-24 |  | danielepaliotta96@gmail.com | https://www.pivotaltracker.com/story/show/157840373 | danielepaliotta96@gmail.com
157897177 | Web scraper to download image for dataset. | model | 2 | 2018-05-21 | 2018-05-27 | chore |  | accepted | 2018-05-27 | 2018-05-27 |  | danielepaliotta96@gmail.com | https://www.pivotaltracker.com/story/show/157897177 | danielepaliotta96@gmail.com
157671359 | controller creation |  | 3 | 2018-05-28 | 2018-06-03 | chore |  | accepted | 2018-05-17 | 2018-05-29 |  | luca.ferrera96@gmail.com | https://www.pivotaltracker.com/story/show/157671359 | luca.ferrera96@gmail.com
157684987 | Add admin role to database | admin, authentication | 3 | 2018-05-28 | 2018-06-03 | feature | 1 | accepted | 2018-05-18 | 2018-05-29 |  | Daniele Cappuccio | https://www.pivotaltracker.com/story/show/157684987 | Daniele Cappuccio
157823674 | Write down acceptance tests to use alongside cucumber | cucumber, testing | 3 | 2018-05-28 | 2018-06-03 | feature | 1 | accepted | 2018-05-23 | 2018-05-29 |  | Daniele Cappuccio | https://www.pivotaltracker.com/story/show/157823674 | Daniele Cappuccio | luca.ferrera96@gmail.com
157934258 | Add profile retrieving backend-side | backend, profiles | 3 | 2018-05-28 | 2018-06-03 | feature | 1 | accepted | 2018-05-29 | 2018-05-29 |  | Daniele Cappuccio | https://www.pivotaltracker.com/story/show/157934258 | Daniele Cappuccio
158055741 | endpoint for retrieving all information from models | backend | 4 | 2018-06-04 | 2018-06-10 | chore |  | accepted | 2018-06-03 | 2018-06-05 |  | luca.ferrera96@gmail.com | https://www.pivotaltracker.com/story/show/158055741 | luca.ferrera96@gmail.com
158056858 | As Logged User I want to Upload picture of landmark or monument visited so that the app can recognize it and validate it. | backend, landmark_detection | 4 | 2018-06-04 | 2018-06-10 | feature | 3 | accepted | 2018-06-03 | 2018-06-09 |  | luca.ferrera96@gmail.com | https://www.pivotaltracker.com/story/show/158056858 | luca.ferrera96@gmail.com
158118419 | As User I want to know which landmarks I've visited |  | 4 | 2018-06-04 | 2018-06-10 | feature | 1 | accepted | 2018-06-05 | 2018-06-09 |  | luca.ferrera96@gmail.com | https://www.pivotaltracker.com/story/show/158118419 | luca.ferrera96@gmail.com
157672354 | Add mailer to confirm registration of new users |  | 4 | 2018-06-04 | 2018-06-10 | feature | 2 | accepted | 2018-05-17 | 2018-06-09 |  | Daniele Cappuccio | https://www.pivotaltracker.com/story/show/157672354 | Daniele Cappuccio
157896946 | Baseline model for landmark recognition. | model | 4 | 2018-06-04 | 2018-06-10 | feature | 2 | accepted | 2018-05-26 | 2018-06-09 |  | danielepaliotta96@gmail.com | https://www.pivotaltracker.com/story/show/157896946 | danielepaliotta96@gmail.com
158241323 | Password update for users | password, user | 4 | 2018-06-04 | 2018-06-10 | feature | 2 | accepted | 2018-06-10 | 2018-06-10 |  | Daniele Cappuccio | https://www.pivotaltracker.com/story/show/158241323 | Daniele Cappuccio
158239674 | Admin dashboard with all Admin's stories | admin, backend, frontend | 4 | 2018-06-04 | 2018-06-10 | feature | 2 | accepted | 2018-06-10 | 2018-06-11 |  | luca.ferrera96@gmail.com | https://www.pivotaltracker.com/story/show/158239674 | danielepaliotta96@gmail.com | luca.ferrera96@gmail.com
158239676 | User profile page | backend, frontend | 4 | 2018-06-04 | 2018-06-10 | feature | 3 | accepted | 2018-06-10 | 2018-06-11 |  | luca.ferrera96@gmail.com | https://www.pivotaltracker.com/story/show/158239676 | luca.ferrera96@gmail.com | danielepaliotta96@gmail.com